## Sheet1
Task | Completion date | Research Question
Literature review: - Currently used policy instruments. - Policy coherence concepts and assessments. - Sustainability targets at different scales. -Land-use change drivers | February 2020 | Research question 1
MAgPIE adjustments and modifications, including validation functions | May 2020
MAgPIE runs | July 2020
Paper ready for submission | September 2020
Literature review: - Global Market perspective of the agricultural sector. - Elements of trading policies. - Sustainability in a telecoupled world. | December 2020 | Research question 2
MAgPIE adjustments and modifications, including validation functions | March 2021
MAgPIE runs | May 2021
Paper ready for submission | July 2021
Literature review: - Policy design elements. - Policy implementation across different spatial scales. | October 2021 | Research question 3
MAgPIE adjustments and modifications, including validation functions | January 2022
MAgPIE runs | March 2022
Paper ready for submission | May 2022
Dissertation | August 2022 | Completion of thesis